## Warren
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15 |  |  | Base Period
| Employee Name | Warren Kibbe |  |  |  | Funded Effort: |  | 20%
| Lab Category | PI
ID | Task Name | Planned LOE | Start Date | End Date | Avg MR | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management | 192 | 2009-06-16 | 2010-06-15 |  | 16 | [11 empty] | 16 | 8.333%
2 | UC/Requirements, Architect, Design | 96 | 2009-06-16 | 2010-06-15 |  | 8 | [11 empty] | 8 | 8.333%
3 | System Dev./Impl. | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.1 | PSC Template Library | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
4 | QA and Testing | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 96 | 2009-06-16 | 2010-06-15 |  | 4 | [11 empty] | 4 | 4.167%
6 | System Deployment | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
7 | Document Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
8 | Adoptor Activity | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
Total |  | 384 |  |  | 32 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 7.292%
OV % |  | 0% |  |  |  | -12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| RFP Proposed LOE | 192
[6 empty] | 32.3636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sean
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | Sean Whitaker |  |  |  | Funded Effort: |  | 50%
| Lab Category | Project Mgr
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management | 480 | 2009-06-16 | 2010-06-15 |  | 50 | [11 empty] | 50 | 10.42%
2 | UC/Requirements, Architect, Design | 160 | 2009-06-16 | 2010-06-15 |  | 15 | [11 empty] | 15 | 9.375%
3 | System Dev./Impl. | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.1 | PSC Template Library | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
4 | QA and Testing | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 160 | 2009-06-16 | 2010-06-15 |  | 10 | [11 empty] | 10 | 6.25%
6 | System Deployment | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
7 | Document Support | 160 | 2009-06-16 | 2010-06-15 |  | 5 | [11 empty] | 5 | 3.125%
8 | Adoptor Activity | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
Total |  | 960 |  |  | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 8.333%
OV % |  | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
RFP Proposed LOE
[6 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Rhett
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | Rhett Sutphin |  |  |  | Funded Effort: |  | 80%
| Lab Category | Lead Arch/Dev
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management |  | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
2 | UC/Requirements, Architect, Design | 384 | 2009-06-16 | 2010-06-15 |  | 32 | [11 empty] | 32 | 8.333%
3 | System Dev./Impl. | 768 | 2009-06-16 | 2010-06-15 |  | 90 | [11 empty] | 90 | 11.72%
3.1 | PSC Template Library | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
4 | QA and Testing | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 192 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
6 | System Deployment | 192 | 2009-06-16 | 2010-06-15 |  | 6 | [11 empty] | 6 | 3.125%
7 | Document Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
8 | Adoptor Activity | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
Total |  | 1536 |  |  | 128 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 8.333%
|  | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| RFP Proposed LOE |  | 960
[6 empty] | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 1408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Lee
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | Lee Esker |  |  |  | Funded Effort: |  | 5%
| Lab Category | SME/QA
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
2 | UC/Requirements, Architect, Design | 48 | 2009-06-16 | 2010-06-15 |  | 4 | [11 empty] | 4 | 8.333%
3 | System Dev./Impl. | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.1 | PSC Template Library | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
4 | QA and Testing | 48 | 2009-06-16 | 2010-06-15 |  | 4 | [11 empty] | 4 | 8.333%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
6 | System Deployment | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
7 | Document Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
8 | Adoptor Activity | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
Total |  | 96 |  |  | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8.333%
OV % |  | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
RFP Proposed LOE
[6 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Jalpa
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | Jalpa Patel |  |  |  | Funded Effort: |  | 100%
| Lab Category | Developer
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
2 | UC/Requirements, Architect, Design | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3 | System Dev./Impl. | 1920 | 2009-06-16 | 2010-06-15 |  | 160 | [11 empty] | 160 | 8.333%
3.1 | PSC Template Library | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
4 | QA and Testing | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
6 | System Deployment | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
7 | Document Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
8 | Adoptor Activity | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
Total |  | 1920 |  |  | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 8.333%
OV % |  | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| RFP Proposed LOE | 288
[6 empty] | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## David
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | David Patton |  |  |  | Funded Effort: |  | 25%
| Lab Category | SME/QA
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
2 | UC/Requirements, Architect, Design | 240 | 2009-06-16 | 2010-06-15 |  | 20 | [11 empty] | 20 | 8.333%
3 | System Dev./Impl. | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.1 | PSC Template Library | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
4 | QA and Testing | 200 | 2009-06-16 | 2010-06-15 |  | 17 | [11 empty] | 17 | 8.5%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
6 | System Deployment | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
7 | Document Support | 40 | 2009-06-16 | 2010-06-15 |  | 3 | [11 empty] | 3 | 7.5%
8 | Adoptor Activity | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
Total |  | 480 |  |  | 40 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 7.708%
OV % |  | 0% |  |  |  | -7.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| RFP Proposed LOE | 288
[6 empty] | 40.2727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Jignesh
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | Jignesh Patel |  |  |  | Funded Effort: |  | 20%
| Lab Category | System Admin
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
2 | UC/Requirements, Architect, Design | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3 | System Dev./Impl. | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.1 | PSC Template Library | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
4 | QA and Testing | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
6 | System Deployment | 152 | 2009-06-16 | 2010-06-15 |  | 16 | [11 empty] | 16 | 10.53%
7 | Document Support | 40 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
8 | Adoptor Activity | 192 | 2009-06-16 | 2010-06-15 |  | 16 | [11 empty] | 16 | 8.333%
Total |  | 384 |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
OV % |  | 0% |  |  |  | -100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| RFP Proposed LOE | 288
[6 empty] | 34.9091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Nataliya
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | Nataliya Shurupova |  |  |  | Funded Effort: |  | 100%
| Lab Category | Developer
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
2 | UC/Requirements, Architect, Design | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3 | System Dev./Impl. | 1920 | 2009-06-16 | 2010-06-15 |  | 160 | [11 empty] | 160 | 8.333%
3.1 | PSC Template Library | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
4 | QA and Testing | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
6 | System Deployment | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
7 | Document Support | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
8 | Adoptor Activity | 0 | 2009-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
Total |  | 1920 |  |  | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 8.333%
OV % |  | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| RFP Proposed LOE | 1920
| Adjusted Avg |  |  |  |  | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bal | [5 empty] | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chk | [5 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## John
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | John Dzak |  |  |  | Funded Effort: |  | 100%
| Lab Category | Developer
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
2 | UC/Requirements, Architect, Design | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3 | System Dev./Impl. | 1920 | 2010-06-16 | 2010-06-15 |  | 160 | [11 empty] | 160 | 8.333%
3.1 | PSC Template Library | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support | 0 | 2010-06-16 | 2010-06-15 |  | 0 | [11 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
4 | QA and Testing | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
6 | System Deployment | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
7 | Document Support | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
8 | Adoptor Activity | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
Total |  | 1920 |  |  | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 8.333%
OV % |  | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| RFP Proposed LOE | 1920
[6 empty] | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Renee
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | Renee Webb |  |  |  | Funded Effort: |  | 5%
| Lab Category | SME
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
2 | UC/Requirements, Architect, Design | 96 | 2010-06-16 | 2010-06-15 |  | 8 | [11 empty] | 8 | 8.333%
3 | System Dev./Impl. | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.1 | PSC Template Library | 0 | 2010-06-16 | 2010-06-15 |  | 0 | [11 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support |  | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement |  | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
4 | QA and Testing | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
6 | System Deployment | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
7 | Document Support | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
8 | Adoptor Activity | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
Total |  | 96 |  |  | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8.333%
OV % |  | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| RFP Proposed LOE | 1920
[6 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Dong
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | Dong Fu |  |  |  | Funded Effort: |  | 20%
| Lab Category | System Admin
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
2 | UC/Requirements, Architect, Design | 128 | 2010-06-16 | 2010-06-15 |  | 11 | [11 empty] | 11 | 8.594%
3 | System Dev./Impl. | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.1 | PSC Template Library | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2010-06-16 | 2010-06-15 |  | 0 | [11 empty] | 0 | 0%
4 | QA and Testing | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 64 | 2010-06-16 | 2010-06-15 |  | 5 | [11 empty] | 5 | 7.812%
6 | System Deployment | 64 | 2010-06-16 | 2010-06-15 |  | 6 | [11 empty] | 6 | 9.375%
7 | Document Support | 64 | 2010-06-16 | 2010-06-15 |  | 6 | [11 empty] | 6 | 9.375%
8 | Adoptor Activity | 64 | 2010-06-16 | 2010-06-15 |  | 5 | [11 empty] | 5 | 7.812%
Total |  | 384 |  |  | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 4.167%
OV % |  | 0% |  |  |  | -50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
RFP Proposed LOE
[6 empty] | 33.4545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SB-Dev
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | Kruttik Aggarwal |  |  |  | Funded Effort: |  | 100%
| Lab Category | Developer
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09 | Subtotal | % Compl.
1 | Project Management | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
2 | UC/Requirements, Architect, Design | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3 | System Dev./Impl. | 1920 | 2010-06-16 | 2010-06-15 |  | 100 | [11 empty] | 100 | 5.208%
3.1 | PSC Template Library | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.2 | Enterprise Svc Integration Tech Support | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.3 | CCTS 2.0 Support (NES) | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
4 | QA and Testing | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
6 | System Deployment | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
7 | Document Support | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
8 | Adoptor Activity | 0 | 2010-06-16 | 2010-06-15 | [13 empty] | 0 | 0%
Total |  | 1920 |  |  | 160 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 5.208%
OV % |  | 0% |  |  |  | -37.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
RFP Proposed LOE
[6 empty] | 165.4545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 1820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project Summary (hidden)
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
[6 empty] | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | SubTotal | Completion %
ID | Name | Lab Cat | Total LOE | Start | End | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09
1 | Warren Kibbe | PI | 384 | 2009-06-16 | 2010-06-15 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 7.292%
2 | Sean Whitaker | Project Mgr | 960 | 2009-06-16 | 2010-06-15 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 8.333%
3 | Rhett Sutphin | Lead Arch/Dev | 1536 | 2009-06-16 | 2010-06-15 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 8.333%
4 | Jalpa Patel | Developer | 1920 | 2009-06-16 | 2010-06-15 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5 | Nataliya Shurupova | Developer | 1920 | 2009-06-16 | 2010-06-15 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 8.333%
6 | John Dzak | Developer | 1920 | 2009-06-16 | 2010-06-15 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
7 | David Patton | SME/QA | 480 | 2009-06-16 | 2010-06-15 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 7.708%
8 | Jignesh Patel | System Admin | 384 | 2009-06-16 | 2010-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
9 | Renee Webb | SME | 96 | 2009-06-16 | 2010-06-15 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8.333%
10 | Dong Fu | System Admin | 384 | 2009-06-16 | 2010-06-15 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 4.167%
11 | Lee Esker | SME/QA | 96 | 2009-06-16 | 2010-06-15 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8.333%
12 | Kruttik Aggarwal | Developer | 1920 | 2009-06-16 | 2010-06-15 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 5.208%
Total |  |  | 12000 |  |  | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Accumulated Mon | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontractor Information |  |  | Total LOE | Start | End
Type | Adopters
Name | Category

## Milestones (hidden)
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
Milestone | ID | Task | Planned LOE | Start | End | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Subtotal | % Compl.
[6 empty] | 06/30/09 | 07/31/09 | 08/31/09 | 09/30/09 | 10/31/09 | 11/30/09 | 12/30/09 | 01/31/10 | 02/27/10 | 03/31/10 | 04/30/10 | 05/31/09
| 1 | Project Management | 672 | 2009-06-16 | 2010-06-15 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 9.821%
| 2 | UC/Requirements, Architect, Design | 912 | 2009-06-16 | 2010-06-15 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 8.553%
| 3 | System Dev./Impl. | 8448 | 2009-06-16 | 2010-06-15 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570 | 6.747%
| 3.1 | PSC Template Library | 0 | 2009-06-16 | 2010-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| 3.2 | Enterprise Svc Integration Tech Support | 0 | 2009-06-16 | 2010-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| 3.3 | CCTS 2.0 Support (NES) | 0 | 2009-06-16 | 2010-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| 3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2009-06-16 | 2010-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| 4 | QA and Testing | 48 | 2009-06-16 | 2010-06-15 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8.333%
| 5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 512 | 2009-06-16 | 2010-06-15 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 3.711%
| 6 | System Deployment | 256 | 2009-06-16 | 2010-06-15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4.688%
| 7 | Document Support | 224 | 2009-06-16 | 2010-06-15 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 4.911%
| 8 | Adoptor Activity | 64 | 2009-06-16 | 2010-06-15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7.812%
Total |  |  | 11136 |  |  | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 6.87%
OV % |  |  | 0% | 928 |  | -21.31% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Adjusted Avg | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Chk |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SB-Manager
Project Name |  | PSC- Northwestern University with SemanticBits | [7 empty] | Start | 2009-06-16 | End | 2010-06-15
| Employee Name | Ram Chilukuri |  |  |  | Funded Effort: |  | 10%
| Lab Category | Manager
ID | Task Name | Planned LOE | Start Date | End Date |  | 07/15/09 | 08/15/09 | 09/15/09 | 10/15/09 | 11/15/09 | 12/15/09 | 01/15/09 | 02/15/10 | 03/15/10 | 04/15/10 | 05/15/10 | 06/15/09
1 | Project Management | 192 | 2010-06-16 | 2010-06-15 |  | 16
2 | UC/Requirements, Architect, Design | 0 | 2010-06-16 | 2010-06-15
3 | System Dev./Impl. | 0 | 2010-06-16 | 2010-06-15
3.1 | PSC Template Library | 0 | 2010-06-16 | 2010-06-15
3.2 | Enterprise Svc Integration Tech Support | 0 | 2010-06-16 | 2010-06-15
3.3 | CCTS 2.0 Support (NES) | 0 | 2010-06-16 | 2010-06-15
3.4 | PSC Feature Support include Mobile Svc, Mult-site, and other enhancement | 0 | 2010-06-16 | 2010-06-15
4 | QA and Testing | 0 | 2010-06-16 | 2010-06-15
5 | caBIG Compliance - SLC, BAM, BRIDG, 508, HIPPA, FDA-21CFR11 | 0 | 2010-06-16 | 2010-06-15
6 | System Deployment | 0 | 2010-06-16 | 2010-06-15
7 | Document Support | 0 | 2010-06-16 | 2010-06-15
8 | Adoptor Activity | 0 | 2010-06-16 | 2010-06-15
Total |  | 192 |  |  | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OV % |  | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
RFP Proposed LOE
[6 empty] | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0